## RFC Management Tracker
RFC Management Tracker | [7 empty] | AMuN Manager : Salma Rechad Date of Last Update : 30-May
PRIORITY | STATUS | PROJECT & REQUEST TYPE | DESCRIPTION | RESPONSIBLE | REQUEST DATE | RESPONSE DATE | FOLLOW-UP DATE | REMARKS | REQUEST NATURE | PROGRAM IMPACT | FISE FEE IMPACT
FR.PAR |  | BE.BRU2
| PENDING | request of change 4 | Changing in Type of Chiller - IND A | AMUN
CH.GVA1
PAR.AUB2
SP.MAD1
SW.ZRH1
All sites

## RFI Management Tracker
RFI Management Tracker | [7 empty] | AMuN Manager : Salma Rechad Date of Last Update : 30-May
PRIORITY | STATUS | PROJECT & REQUEST TYPE | DESCRIPTION | RESPONSIBLE | REQUEST DATE | RESPONSE DATE | FOLLOW-UP DATE | REMARKS | REQUEST NATURE | PROGRAM IMPACT | FISE FEE IMPACT | STATUS | PRIORITY
|  | BE.BRU2 | [9 empty] | On Hold | LOW
[12 empty] | Pending approval | MED
|  | CH.GVA1 | [9 empty] | In Progress
PAR.AUB2
SP.MAD1
SW.ZRH1
All sites
HIGH | On Hold | Request for Information 1 | Missing documents for the Security parts. | nLighten | 2025-05-15 | 2025-05-27 | 2025-05-21 | nLighten returned the analyzed standards without comments on the GAP Analysis. They added new documents.
HIGH | On Hold | Request for Information 2 | Missing documents for the BMS parts. | nLighten | 2025-05-15 | 2025-05-27 | 2025-05-21 | nLighten returned the analyzed standards without comments on the GAP Analysis. They added new documents.
HIGH | On Hold | Request for Information 3 | HVAC power supply. | nLighten | 2025-05-26