## Change Order Request
2 | STANDARDS EXCEPTION REQUEST |  | Change n° | 004
2 | PROJECT SCOPE CHANGE REQUEST
2 | PROCEDURE / CONTRACTUAL CHANGE REQUEST
1. APPLICATION OF REQUEST
Select area of application:
Project code |  |  | City
Date of proposal |  |  | Initiator (Name & Company)
Contact email
2. REQUEST INFORMATION
Headline identification:
Changing in Type of Chiller - IND A
Initial scope / Situation
Background/ justification / reason for change:
Proposed change: final scope / Situation
Consequences of change and mitigation of potential risks:
Impacts: |  | Y/N | Impacts / Mitigations:
Design: |  | YES
Permit / Administrative: |  | YES
Procurement: |  | YES
Costs: |  | YES
Planning: |  | YES
Health & Safety: |  | NO
Quality: |  | NO
Programme: |  | NO
Business / Operation: |  | YES
Attachments:
1 | Layouts
2
3
4
5
Reply date |  |  | Accepted / Rejected
Reply by |  |  | Signature
No design or construction work using the change request must commence before the case is approved
Completed change request cases must be archived including Approvals and ALL attachments.