## RFC Management Tracker
RFC Management Tracker | [7 empty] | AMuN Manager : Salma Rechad Date of Last Update : 30-May
PRIORITY | STATUS | PROJECT & REQUEST TYPE | DESCRIPTION | RESPONSIBLE | REQUEST DATE | RESPONSE DATE | FOLLOW-UP DATE | REMARKS | REQUEST NATURE | PROGRAM IMPACT | FISE FEE IMPACT
BE.BRU2
HIGH | Pending approval | Change Request 1 | Replacement of existing DX on DC5. | nLighten | 2025-04-29 |  | 2025-05-14 | Already incorporated within RIBA2 | Design Development | NO
HIGH | Pending approval | Change Request 2 | Position of the New transformers. | nLighten | 2025-05-14 |  |  | Already incorporated within RIBA2 | Design Development | NO
HIGH | Pending approval | Change Request 3 | Replacement of existing Pumps. | nLighten | 2025-05-14 |  |  | Already incorporated within RIBA2 | Design Development | NO
CH.GVA1
HIGH | On Hold | Change Request 1 | High Density Rack Deployment | AMuN |  |  |  |  | Scope Change | YES | Yes
PAR.AUB2
HIGH | On Hold | Change Request 1 | Chiller Type | nLighten | 2025-05-30 |  |  |  | Design Development | NO | NO
HIGH | On Hold | Change Request 2 | Generator Power | AMuN |  |  |  |  | Design Development | NO | NO
HIGH | On Hold | Change Request 3 | Phasing - Phase1&2 Merged | AMuN |  |  |  |  | Scope Change | NO | NO
HIGH | On Hold | Change Request 4 | DC2 early Deployment | AMuN |  |  |  |  | Scope Change | YES | YES
HIGH | On Hold | Change Request 5 | DC5 DC6 feasibiity study | AMuN |  |  |  |  | Scope Change | YES | YES
SP.MAD1
HIGH | On Hold | Change Request 1 | Early deploymen for C4 et D1 | AMuN |  |  |  |  | Scope Change | YES | YES
SW.ZRH1
All sites

## RFI Management Tracker
RFI Management Tracker | [7 empty] | AMuN Manager : Salma Rechad Date of Last Update : 30-May
PRIORITY | STATUS | PROJECT & REQUEST TYPE | DESCRIPTION | RESPONSIBLE | REQUEST DATE | RESPONSE DATE | FOLLOW-UP DATE | REMARKS | REQUEST NATURE | PROGRAM IMPACT | FISE FEE IMPACT | STATUS | PRIORITY
|  | BE.BRU2 | [9 empty] | On Hold | LOW
[12 empty] | Pending approval | MED
|  | CH.GVA1 | [9 empty] | In Progress
PAR.AUB2
SP.MAD1
SW.ZRH1
All sites
HIGH | On Hold | Request for Information 1 | Missing documents for the Security parts. | nLighten | 2025-05-15 | 2025-05-27 | 2025-05-21 | nLighten returned the analyzed standards without comments on the GAP Analysis. They added new documents.
HIGH | On Hold | Request for Information 2 | Missing documents for the BMS parts. | nLighten | 2025-05-15 | 2025-05-27 | 2025-05-21 | nLighten returned the analyzed standards without comments on the GAP Analysis. They added new documents.
HIGH | On Hold | Request for Information 3 | HVAC power supply. | nLighten | 2025-05-26